## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2026-06-24 | 2026-07-13 | 95% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 95% | Giảng Thanh Danh | Missing padding before and after transition
Logo | 2026-06-24 | 2026-07-13 | 80% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 80% | Giảng Thanh Danh | Missing URL to Home
Navbar | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Submenu | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Search button | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Theme Button | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Homepage | 2026-06-24 | 2026-07-13 | 85% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 85% | Giảng Thanh Danh
Banner Carousel | 2026-06-24 | 2026-07-13 | 40% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 40% | Giảng Thanh Danh | Banner incompleted
About Us | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Features | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Services | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Gallery | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Progress Bar | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Testimonials | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Blogs | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Styling | 2026-06-24 | 2026-07-13 | 100% | Giảng Thanh Danh | 2026-07-12 | 2026-07-14 | 100% | Giảng Thanh Danh
About Us | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-15 | 100% | Giảng Thanh Danh
Hero Banner | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-16 | 100% | Giảng Thanh Danh
About Company | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
About Page Stat | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Video Section | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Professional | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Why Choose | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
CTA | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Styling | 2026-06-25 | 2026-07-13 | 50% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh | Fixed CSS Layout to Bootstrap
|  |  | 50% | Giảng Thanh Danh
Services | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-15 | 100% | Giảng Thanh Danh
Hero Banner | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-16 | 100% | Giảng Thanh Danh
About Company | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
About Page Stat | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Video Section | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Professional | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Why Choose | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
CTA | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh
Styling | 2026-06-25 | 2026-07-13 | 100% | Phạm Nguyễn Tuyết Phương | 2026-07-12 | 2026-07-13 | 100% | Giảng Thanh Danh | Fixed CSS Layout to Bootstrap